## Sheet1
Failure Mode # | Subsystem | Failure Mode | Failure Effects | Possible Cause | Failure Effects Severity | Occurrence Likelihood | Risk Priority Number (RPN) (=severity * occurrence) | Risk Criticality (Corrective Action Priority) | Corrective Action | Failure Effects Severity | Occurrence Likelihood | Risk Priority Number (RPN) | Criticality (Corrective Action Priority) | Corrective Action Effort | Corrective Action | Failure Effects Severity | Occurrence Likelihood | Risk Priority Number (RPN) | Criticality (Corrective Action Priority) | Corrective Action Effort | Troubleshooting (optional)
F.1 | IR Sensor Encoder | Reported number of rotations from the IR sensor is too few | Demand incorrectly larger than necessary, Energy usage is larger than necessary, Bicycle goes far faster than desired | sensor detector or emitter is partially blocked or damaged, | 4 | 5 | 20 | HIGH | Add a shielding cone to the detector. Add a sweep to the emitter just before it passes the detector to help clear the emitter off. Increase the intensity of the emitter. Research more robust parts. Put in a redundant encoder and adjust sensor filter system to account for this redundancy. Ensure manual override system is functioning properly. | 4 | 2 | 8 | MEDIUM | 15 hrs. (See Timeline's IR Sensor Risk Plan B) | Use COTS Encoder. Put in a redundant encoder and adjust sensor filter system to account for this redundancy. Ensure manual override system is functioning properly. | 4 | 1 | 4 | MEDIUM LOW | 10 hrs. (See Timeline's IR Sensor Risk Plan E) | Check encoders to make sure they are securely fastened and properly aligned. Check encoders for debris and clean if need be. Check encoders to make sure they're still working. Replace encoders if need be.
|  |  |  | sensor detector or emitter is damaged | 4 | 2 | 8 | MEDIUM | Research more robust parts. Put in a redundant encoder and adjust sensor filter system to account for this redundancy. Ensure manual override system is functioning properly. | 4 | 1 | 4 | MEDIUM LOW | 12 hrs. (See Timeline's IR Sensor Risk Plan B)
|  |  |  | sensor detector or emitter has become loose or is no longer oriented properly | 4 | 4 | 16 | MEDIUM HIGH | Increase the robustness of the mechanical housing. Included checking its secureness as part of the recommended start up safety check. Put in a redundant encoder and adjust sensor filter system to account for this redundancy | 4 | 1 | 4 | MEDIUM LOW | 12 hrs. (See Timeline's IR Sensor Risk Plan B and Plan C)
F.2 |  | Reported number of rotations from the IR sensor is too many | Demand incorrectly as smaller than necessary, Energy storage is conserved or even increased more than it should be, Bicycle goes far slower than desired | sensor detector or emitter is partially damaged | 2 | 1 | 2 | LOW | [12 empty] | Check encoders to make sure they are securely fastened and properly aligned. Check encoders for debris and clean if need be. Check encoders to make sure they're still working. Replace encoders if need be.
F.3 |  | No signal provided | Sensor Filter System reports error. Demand Algorithm Reports Error. Controller switches to energy storage only, no usage. GUI reports error. Bicycle functions inefficiently until user disengages PMB engine | broken detector or emitter | 2 | 2 | 4 | MEDIUM LOW | Research more robust parts. Put in a redundant encoder and adjust sensor filter system to account for this redundancy. | 2 | 1 | 2 | LOW | 12 hrs. (See Timeline's IR Sensor Risk Plan B) | [6 empty] | Check encoders to make sure they are securely fastened and properly aligned. Check wiring for frays and proper connections. Replace encoders or connections if need be.
|  |  |  | power cables disconnected | 2 | 4 | 8 | MEDIUM | Increase the robustness of the mechanical housing to take stress of cable connections | 2 | 1 | 2 | LOW | 3 Hrs. (See Timeline's IR Sensor Risk Plan D)
|  |  |  | signal cables disconnected | 2 | 5 | 10 | MEDIUM | Increase the robustness of the mechanical housing to take stress of cable connections | 2 | 1 | 2 | LOW | 3 Hrs. (See Timeline's IR Sensor Risk Plan D)